## Sheet1
Group Name | Team Members | March |  |  |  | April |  |  |  | May |  |  |  | June
|  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | Notes
WP 1: Back-end_Employee_1 Manager: Jiang Zexin | Jiang Zexin
Task 1.1: Analyse the requirements of the employee aspects. | Liu Haoran
Task 1.2: Design the architectures of the relevant part of the project. | Yu Jiayue
Task 1.3: Complete the functions on the back-end. | Long Min
Task 1.4: Connect with the front-end UI
Task 1.5: Test the whole project
WP 2: Back-end _Emloyee_2 Manager: Liu Haoran | Liu Haoran
Task 2.1: Analyse requirements of the project | Jiang Zexin
Task 2.2: Design basing on requirements analysis | Yu Jiayue
Task 2.3: Implement functions of the back end of employee’s function | Long Min
Task 2.4: Connect to the database
Task 2.5 Connect to the front end
WP3: Back-end_Customer Manager: Zheng Zhi | Zheng Zhi
Task 3.1: Analyse customer’s requirements | Xu Ziting
Task 3.2: Design | Long Min
Task 3.3: Achieve all the functionalities
Task 3.4: Connect to the front-end
Task 3.5 Project integration and testing
WP4: Front-end_Employee Manager: Yu Jiayue | Yu Jiayue
Task 4.1: Analyse user requirements | Jiang Zexin
Task 4.2: Design the layout of website pages | Liu Haoran
Task 4.3: Write code to realize the User Interface | Xu Ziting
Task 4.4: Test the implementation of the employee-side website
Task 4.5 Test the communication between the employee and the customer side
WP 5: Front-end _Customer Manager:Xu Ziting | Xu Ziting
Task 5.1: Analyse user requirements | Yu Jiayue
Task 5.2: Design the website layout based on the requirements | Zheng Zhi
Task 5.3: Write code to accomplish the User Interface of customers
Task 5.4: Write code to help the back-end implementation
Task 5.5: Test the implementation of the entire website
WP 6: Back-end _Databases Manager: Long Min | Long Min
Task 6.1: Requirements analyse | Jiang Zexin
Task 6.2: Design | Zheng Zhi
Task 6.3: Implement | Liu Haoran
Task 6.4: Deploy
Task 6.5: Test