## Sheet1
Group Name | Team Members | March |  |  |  | April |  |  |  | May |  |  |  | June
|  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | Notes
WP 1: Back-end_Employee_1 Manager: Jiang Zexin | Jiang Zexin
Task 1.1: Requirement analysis and architecture design on the employees' side | Liu Haoran
Task 1.2: Login & register database design and implementation | Yu Jiayue
Task 1.3: Online chatting between customers and employees implementation | Long Min
Task 1.4: Employees handling with all the appointments implementation
Task 1.5: Cloud server and non-functional requirements implementation
Task 1.6: Test first beta of the system
WP 2: Back-end _Emloyee_2 Manager: Liu Haoran | Liu Haoran
Task 2.1: Requirement analysis and architecture design on the employees' side | Jiang Zexin
Task 2.2: Login & register database design and implementation | Yu Jiayue
Task 2.3: Online chatting between customers and employees implementation | Long Min
Task 2.4: Employees sending notifications implementation
Task 2.5: Cloud server and non-functional requirements implementation
Task 2.6: Test first beta of the system
WP3: Back-end_Customer Manager: Zheng Zhi | Zheng Zhi
Task 3.1: Requirement analysis and architecture design on the customers' side | Xu Ziting
Task 3.2: Customers profile design and implementation | Long Min
Task 3.3: Appointments database design
Task 3.4: Customers making appointments implementation
Task 3.5: Customers seeing the status of pets implementation
Task 3.6: Test first beta of the system
WP4: Front-end_Employee Manager: Yu Jiayue | Yu Jiayue
Task 4.1: Requirement analysis and architecture design on the employees' side | Jiang Zexin
Task 4.2: Login & register interface design | Liu Haoran
Task 4.3: Emloyees interface implementation | Xu Ziting
Task 4.4: Employees appointments handling implementation
Task 4.5: Cloud server and non-functional requirements implementation
Task 4.6: Test first beta of the system
WP 5: Front-end _Customer Manager:Xu Ziting | Xu Ziting
Task 5.1: Requirement analysis and architecture design on the customers' side | Yu Jiayue
Task 5.2: Login & register interface design | Zheng Zhi
Task 5.3: Customers interface implementation
Task 5.4: Customers making appointments implementation
Task 5.5: Customers seeing the status of pets implementation
Task 5.6: Test first beta of the system
WP 6: Back-end _Databases Manager: Long Min | Long Min
Task 6.1: Requirement analysis and architecture design on both side | Jiang Zexin
Task 6.2: User login & register database design and implementation | Zheng Zhi
Task 6.3: Customer profile database design | Liu Haoran
Task 6.4: Appointments database design
Task 6.5: Cloud server and non-functional requirements implementation
Task 6.6: Test first beta of the system
deliverable
milestone